Collection of basic information note 1
(5 days)

Access to basic information

Note 1: Documents or procedures not required by the application for construction permit. The applicant may proceed with it to his sole discretion.
Countersigning at the Counter (Hydraulic Engineering office/TPC/Designated telecommunication operator)

(5 days)

Submission of application for construction permit
(Correction or withdrawal)
Before construction

Counter (Taipei City Construction Management Office) /Department of Environmental Protection/Public Works Department/Taipei City Fire Department/Department of Civil Affairs/Hydraulic Engineering Office/THSR/RTS

Conformance

 (11.5 days)

Counter (Taipei City Construction Management Office)
Pay government fees
Approve commencement of work
(1 day)
Conformance
Counter (Taipei City Construction Management Office)
Receipt of registered mail
(0.5 day)
Joint review prior to commencement of work
(7 days)
Issue construction permit
Pay government fees
(1 day)
Joint Review
(10 days)
Counter (Taipei City Construction Management Office) /THSR/RTS/Public Works Department/Department of Cultural Affairs/Department of Transportation/Department of Land/Department of Urban Development

 Counter (Taipei City Construction Management Office)
Receipt of registered mail
(0.5 day)
Counter (Taipei City Construction Management Office) /Public Works Department/Taipei City Fire Department/Department of Environmental Protection/Hydraulic Engineering Office/THSR/RTS
Counter (Taipei City Construction Management Office)
Conformance

Rejected, in the case of defective qualification or incomplete documents
Non-conformance
Non-conformance
(Correction or withdrawal)

Rejected, in the case of defective qualification or incomplete documents
Joint Survey
(10 days)

Submission of application for completion of work

Approve occupation license
Pay government fees/supply of water
(3 days)
Counter (Taipei City Construction Management Office)/Hydraulic Engineering Office
Department of Land (local land offices)
Designated telecommunication operator
Application for telecommunication devices
(3 days)

Completion and occupation of the building
Commencement of work

Registration of property rights
(18 days, including 15 days for public announcement)
 (33.5 days)

 (8 days)

After completion of work